## DEVELOPMENT LOG
DEVELOPMENT LOG
PROJECT NAME | Predictive Models for Student Placement and Graduation Year
PROJECT MANAGER | Harshada Topale
PROJECT DELIVERABLE | To develop a predictive model that forecasts students' year of graduation and their chances of securing job placements.
PROJECT SCOPE | Addressing the lack of clear academic planning and career advice to improve timely graduation rates and enhance student employability.
PROJECT START DATE | 2024-06-04
PROJECT END DATE | 2024-06-14
OVERALL PROGRESS | Completed
Date | Task/Activity | Status | Owner | Priority | Time Spent | Comments/Notes | Next Steps | Issues/Risks | Dependencies
2024-06-07 | Data Loading | Completed | User | High | 1 hour | Loaded data from Excel files | - | None | None
2024-06-07 | Data Preprocessing | Completed | User | High | 3 hours | Imputed missing values, handled NaNs | Proceed with feature engineering | Mixed data types in columns | Cleaned data
2024-06-08 | Feature Engineering | In Progress | User | High | 2 hours | Created new features from existing data | Continue feature engineering and EDA | Potential feature redundancy | Preprocessed dataset
2024-06-08 | Model Training | Completed | User | Critical | 4 hours | Encountered errors due to NaN values | Resolve NaN issues and retrain model | NaN values in training data | Cleaned and engineered features
2024-06-09 | Model Training with Pipeline | Completed | User | Critical | 3 hours | Used pipeline to handle preprocessing and training | Evaluate model performance | Mixed data types and missing values | Preprocessed dataset
2024-06-09 | Model Evaluation | In Progress | User | High | 2 hours | Evaluating model performance metrics | Finalize model evaluation | Model performance uncertainty | Trained model
2024-06-10 | Model Prediction | Completed | User | High | 2 hours | Predicted placement status of students with high accuracy of around 90%, and calculated year of graduation | Predict placement status on test data | Potential prediction errors | Trained model
2024-06-10 | Result Analysis and Output Generation | Completed | User | Moderate | 2 hours | Ensured the output file was in the correct format with all the required columns | Generate final output file | Data integrity and format issues | Predicted outcomes