## Sheet1
PROJECT PLAN FOR EXECUTION PHASE
PROJECT NAME | Predictive Models for Student Placement and Graduation Year
PROJECT MANAGER | Harshada Topale
PROJECT DELIVERABLE | To develop a predictive model that forecasts students' year of graduation and their chances of securing job placements.
PROJECT SCOPE | Addressing the lack of clear academic planning and career advice to improve timely graduation rates and enhance student employability.
PROJECT START DATE | 2024-06-04
PROJECT END DATE | 2024-06-14
OVERALL PROGRESS | Completed
Sr No | Week/Duration | Activities | Task | Sub Task | Assigned to | Start Date | End Date | Hours required | Status
1 | Week 1 | INITIATION | Project Charter |  | Roshan Panda | 2024-06-05 | 2024-06-05 | 2-3 | COMPLETED
1.1 |  |  | SRS Document |  | Roshan Panda | 2024-06-05 | 2024-06-05 | 1 | COMPLETED
2 | Week 1-2 | PLANNING | WBS |  | Roshan Panda | 2024-06-06 | 2024-06-06 | 1 | COMPLETED
2.1 |  |  | Project Schedule |  | Roshan Panda | 2024-06-10 | 2024-06-10 | 3 | COMPLETED
2.2 |  |  | RAID Logs |  | Roshan Panda | 2024-06-10 | 2024-06-10 | 2 | COMPLETED
3 | Week 2 | EXECUTION & MONITORING | Design | Design Specification | Roshan Panda | 2024-06-08 | 2024-06-10 | 7-8 | COMPLETED
3.1 |  |  | Develop | Code | Roshan Panda | 2024-06-07 | 2024-06-10 | 7-8 | COMPLETED
3.2 |  |  | Test | Test Plan | Roshan Panda | 2024-06-07 | 2024-06-07 | 5-6 | COMPLETED
3.3 |  |  |  | Test Results | Roshan Panda | 2024-06-09 | 2024-06-10 | 7-8 | COMPLETED
3.4 |  |  | Deploy | App Video | Roshan Panda | 2024-06-10 | 2024-06-10 | 1 | COMPLETED
4 | Week 2 | CLOSURE | Lessons Learnt Project Report |  | Roshan Panda | 2024-06-10 | 2024-06-10 | 4 | COMPLETED