## RAID LOG
| RAID Log | [9 empty] | Total | Critical | High | Moderate | Low | Negligible
[10 empty] | Risk | 7 | 1 | 4 | 2 | 0 | 0 | Instruction to use the RAID log template: • All fields must be duly filled • The descriptions for what to be filled in each of the fields are provided in the template. • Clear all the sample data/instructions provided in the template. The data/instruction provided is only for reference purposes. • Understand what risks, assumptions, issues, and dependencies are from the description provided in the methodology document • Select the category of RAID from the dropdown menu provided in the “RAID category” field in the template. • Provide a valid description of the RAID category that you have selected in the “description” field provided. • Describe the impact the RAID category you have selected will have on the project in the “impact field”. • Describe how the impact of the selected RAID category can be reduced on the project in the “mitigation field” in the template. • Mention the responsible person for working on the selected RAID category in the “owner” field in the template. • Select the priority with which the selected RAID category needs to be mitigated. The following levels of priority are given in the drop-down menu. Select; o Negligible: if the RAID category is not going to make an impact on the project o Low: if the raid category is going to make very small impacts on the project o Moderate: if the RAID category is going to make a few impacts which can affect the project adversely. o High: if the RAID category is going to make major impacts on the project adversely. o Critical: if the raid category is going to affect the project at any stage. • Provide risk priority number based on the priority selected for the RAID category selected. • Select the status of the RAID category selected. Two options are provided in the drop-down menu. Select; o Open: if the responsible person is still working on the RAID category selected. o Closed: if the responsible person has worked on the RAID category and is solved.
| Project title: | Predictive Models for Student Placement and Graduation Year |  |  |  | Project Manager: | Harshada Topale |  |  | Assumption | 3 | 0 | 0 | 3 | 0 | 0
[10 empty] | Issue | 5 | 0 | 0 | 0 | 0 | 0
|  |  |  | Last Updated date: | 2024-06-10 | Project Team Lead: | Roshan Panda |  |  | Dependency | 2 | 0 | 2 | 0 | 0 | 0
| Select … |  |  |  |  | Select … | Risk Priority Number | Open/Closed |  |  | 17 |  |  |  |  | 12
| RAID Category | Description | Impact | Mitigation | Owner | Priority | RPN (for risks) | Status
1 | Risk | Incorrect handling of NaN values in the dataset | Model training failure and inaccurate predictions | Ensure proper imputation strategies and handle NaNs using SimpleImputer or drop NaNs if necessary | User | High | 9 | Open | Risk
2 | Risk | Mixed data types in the same column (e.g., strings and numbers) | Errors in data processing and transformation | Convert all data to a consistent type, use FunctionTransformer and proper data type conversions | User | High | 8 | Open | Assumption
3 | Assumption | Data columns contain uniform data types | Assumes smooth processing and transformation | Verify and enforce data type consistency before processing | User | Moderate | N/A | Open | Issue
4 | Issue | Missing FunctionTransformer import causing code failure | Halts the execution of the pipeline | Ensure all necessary libraries and functions are imported at the beginning of the script | User | Critical | N/A | Closed | Dependency
5 | Issue | ValueError due to presence of non-numeric values in columns expected to be numeric | Stops the model training process | Identify and separate numeric and categorical columns correctly, ensure proper data validation | User | Critical | N/A | Closed
6 | Dependency | Availability of clean and well-structured training and test data | Accurate model training and predictions | Perform thorough data cleaning, preprocessing, and validation before using the data | User | High | N/A | Open | Open
7 | Issue | Errors in fitting the model due to NaN values | Model cannot be trained | Implement robust NaN handling strategies, use pipelines to manage preprocessing and training | User | Critical | N/A | Closed | Closed
8 | Risk | Inconsistent data formats in test and training datasets | Inaccurate predictions and model evaluation | Ensure both datasets are preprocessed similarly, validate data consistency before model training | User | High | 7 | Open
9 | Assumption | The provided datasets have all necessary features for placement prediction | Assumes no need for feature engineering or additional data collection | Review datasets for completeness and relevance, perform feature engineering if necessary | User | Moderate | N/A | Open | Critical
10 | Risk | Imbalanced dataset affecting model performance | Biased predictions towards the majority class | Use techniques like SMOTE, ADASYN, or class weights to handle imbalanced data | User | High | 9 | Open | High
11 | Issue | Errors in one-hot encoding categorical variables | Incorrect feature representation and model errors | Validate the one-hot encoding process, ensure all categories are correctly encoded | User | High | N/A | Closed | Moderate
12 | Dependency | Dependencies on external libraries and packages | Code failures if packages are not installed or updated | Ensure all dependencies are listed and properly installed, maintain a requirements file | User | High | N/A | Open | Low
13 | Risk | Overfitting due to a high number of features | Poor model generalization on new data | Implement regularization techniques, use cross-validation to monitor model performance | User | Moderate | 8 | Open | Negligible
14 | Assumption | All relevant features are included in the dataset | Missing critical features that impact model accuracy | Perform thorough feature selection, consider domain knowledge for identifying important features | User | Moderate | N/A | Open
15 | Risk | Inadequate feature scaling leading to model convergence issues | Slow or failed model training | Use StandardScaler or MinMaxScaler to normalize feature values | User | Moderate | 7 | Open
16 | Issue | Long training times due to large dataset | Delays in model development and iteration | Optimize code, use dimensionality reduction techniques, consider using more computational resources | User | Moderate | N/A | Closed
17 | Risk | Incorrect label encoding for the target variable | Model predictions are incorrect | Validate the label encoding process, ensure correct mapping of labels | User | Critical | 9 | Open
18
19
20
21
22
23
24