## Sheet1
TRACEABILITY MATRIX
PROJECT NAME | Predictive Models for Student Placement and Graduation Year
PROJECT MANAGER | Harshada Topale
PROJECT DELIVERABLE | To develop a predictive model that forecasts students' year of graduation and their chances of securing job placements.
PROJECT SCOPE | Addressing the lack of clear academic planning and career advice to improve timely graduation rates and enhance student employability.
PROJECT START DATE | 2024-06-04
PROJECT END DATE | 2024-06-14
OVERALL PROGRESS | Completed
Requirement ID | Requirement Description | Source | Design Specification ID | Implementation ID | Test Case ID | Status | Requirement ID2 | Requirement Description2 | Source3 | Design Specification ID4 | Implementation ID5 | Test Case ID6 | Status7 | equirement ID8 | Requirement Description9 | Source10 | Design Specification ID11
R1 | Load and preprocess training data | Project Scope | DS1 | IM1 | TC1 | Done | R1 | Load and preprocess training data | Project Scope | DS1 | IM1 | TC1 | Done | R1 | Load and preprocess training data | Project Scope | DS1
R2 | Load and preprocess test data | Project Scope | DS2 | IM2 | TC2 | Done | R2 | Load and preprocess test data | Project Scope | DS2 | IM2 | TC2 | Done | R2 | Load and preprocess test data | Project Scope | DS2
R3 | Handle missing values in numeric features | Project Scope | DS3 | IM3 | TC3 | Done | R3 | Handle missing values in numeric features | Project Scope | DS3 | IM3 | TC3 | Done | R3 | Handle missing values in numeric features | Project Scope | DS3
R4 | Handle missing values in categorical features | Project Scope | DS4 | IM4 | TC4 | Done | R4 | Handle missing values in categorical features | Project Scope | DS4 | IM4 | TC4 | Done | R4 | Handle missing values in categorical features | Project Scope | DS4
R5 | Encode categorical features | Project Scope | DS5 | IM5 | TC5 | Done | R5 | Encode categorical features | Project Scope | DS5 | IM5 | TC5 | Done | R5 | Encode categorical features | Project Scope | DS5
R6 | Split data into training and testing sets | Project Scope | DS6 | IM6 | TC6 | Done | R6 | Split data into training and testing sets | Project Scope | DS6 | IM6 | TC6 | Done | R6 | Split data into training and testing sets | Project Scope | DS6
R7 | Train RandomForest model | Project Scope | DS7 | IM7 | TC7 | Done | R7 | Train RandomForest model | Project Scope | DS7 | IM7 | TC7 | Done | R7 | Train RandomForest model | Project Scope | DS7
R8 | Predict placement status on test data | Project Scope | DS8 | IM8 | TC8 | Done | R8 | Predict placement status on test data | Project Scope | DS8 | IM8 | TC8 | Done | R8 | Predict placement status on test data | Project Scope | DS8
R9 | Evaluate model accuracy | Project Scope | DS9 | IM9 | TC9 | Done | R9 | Evaluate model accuracy | Project Scope | DS9 | IM9 | TC9 | Done | R9 | Evaluate model accuracy | Project Scope | DS9
R10 | Save output with predicted placement status | Project Scope | DS10 | IM10 | TC10 | Done | R10 | Save output with predicted placement status | Project Scope | DS10 | IM10 | TC10 | Done | R10 | Save output with predicted placement status | Project Scope | DS10
R11 | Create visualizations of data and results | Project Scope | DS11 | IM11 | TC11 | Done | R11 | Create visualizations of data and results | Project Scope | DS11 | IM11 | TC11 | Done | R11 | Create visualizations of data and results | Project Scope | DS11
R12 | Document challenges and resolutions (RAID) | Project Scope | DS12 | IM12 | TC12 | Done | R12 | Document challenges and resolutions (RAID) | Project Scope | DS12 | IM12 | TC12 | Done | R12 | Document challenges and resolutions (RAID) | Project Scope | DS12
R13 | Create development log | Project Scope | DS13 | IM13 | TC13 | Done | R13 | Create development log | Project Scope | DS13 | IM13 | TC13 | Done | R13 | Create development log | Project Scope | DS13
R14 | Create traceability matrix | Project Scope | DS14 | IM14 | TC14 | Done | R14 | Create traceability matrix | Project Scope | DS14 | IM14 | TC14 | Done | R14 | Create traceability matrix | Project Scope | DS14